## Gantt Chart
Company Name: Macchina Paintworks Autocare Services and Carwash
Location: San Fernando, Cebu
Contact No. 0977 037 7510
[6 empty] | NOVEMBER | [12 empty] | DECEMBER | [29 empty] | JANUARY
Task ID | Task Name | START | DURATION(Days) | FINISH | Pred. | 3rd | [5 empty] | 4th | [6 empty] | 1st | [6 empty] | 2nd | [6 empty] | 3rd | [6 empty] | 4th | [8 empty] | 1st | [6 empty] | 2nd | [6 empty] | 3rd
 | time axis 2024-11-18 to 2025-01-21
1 | Planning & Information Gathering | 2024-11-18 | 5 | 2024-11-22 | bar: 2024-11-18 to 2024-11-22
2 | System Design | 2024-11-23 | 3 | 2024-11-25 | 1 | bar: 2024-11-23 to 2024-11-25
3 | Title Approval | 2024-11-24 | 14 | 2024-12-07 | 2 | bar: 2024-11-24 to 2024-12-07
4 | System Development | 2024-12-08 | 14 | 2024-12-21 | 3 | bar: 2024-12-08 to 2024-12-21
5 | System Testing | 2024-12-22 | 7 | 2024-12-28 | 4 | bar: 2024-12-22 to 2024-12-28
6 | System Evaluation | 2024-12-29 | 7 | 2025-01-04 | 5 | bar: 2024-12-29 to 2025-01-04
7 | System Deployment | 2025-01-05 | 2 | 2025-01-06 | 6 | bar: 2025-01-05 to 2025-01-06
8 | System Documentation | 2025-01-07 | 3 | 2025-01-09 | 7 | bar: 2025-01-07 to 2025-01-09
9 | Hardbound Submission | 2025-01-09 | 5 | 2025-01-13 | 8 | bar: 2025-01-09 to 2025-01-13