## Gantt Chart
COMPANY NAME: Macchina Paintworks Autocare Services and Carwash
Location: San Fernando, Cebu
[6 empty] | NOVEMBER | [12 empty] | DECEMBER | [29 empty] | JANUARY
Task ID | Task Name | START | DURATION(Days) | FINISH | Pred. | 3rd | [5 empty] | 4th | [6 empty] | 1st | [6 empty] | 2nd | [6 empty] | 3rd | [6 empty] | 4th | [8 empty] | 1st | [6 empty] | 2nd | [6 empty] | 3rd
 | time axis 2024-11-18 to 2025-01-21
1 | Planning | 2024-11-18 | 5 | 2024-11-22 | bar: 2024-11-18 to 2024-11-22
2 | Project ERP System Approval | 2024-11-23 | 14 | 2024-12-06 | 1 | bar: 2024-11-23 to 2024-12-06
3 | Homepage Module | 2024-12-07 | 3 | 2024-12-09 | 2 | bar: 2024-12-07 to 2024-12-09
4 | Login Module | 2024-12-10 | 3 | 2024-12-12 | 3 | bar: 2024-12-10 to 2024-12-12
5 | CRM and Customer Module | 2024-12-13 | 3 | 2024-12-15 | 4 | bar: 2024-12-13 to 2024-12-15
6 | Owner Module | 2024-12-16 | 3 | 2024-12-18 | 5 | bar: 2024-12-16 to 2024-12-18
7 | Mechanic Module | 2025-01-19 | 3 | 2025-01-21 | 6 | bar: 2024-12-19 to 2024-12-21
8 | Cashier Module | 2025-01-22 | 3 | 2025-01-24 | 7 | bar: 2024-12-22 to 2024-12-24
9 | Car Painting Module | 2025-01-25 | 3 | 2025-01-27 | 8 | bar: 2024-12-25 to 2024-12-27
10 | HR Module | 2024-12-28 | 3 | 2024-12-30 | 9 | bar: 2024-12-28 to 2024-12-30
11 | Inventory Module | 2024-12-31 | 3 | 2025-01-02 | 10 | bar: 2025-01-01 to 2025-01-02
12 | Testing | 2025-01-03 | 3 | 2025-01-05 | 11 | bar: 2025-01-03 to 2025-01-05
13 | Submission | 2025-01-05 | 3 | 2025-01-07 | 12 | bar: 2025-01-05 to 2025-01-07